## test_plan_template
Test | Description | Status | Progress | Responsible | Location | Blocker
Connection FMO | Anmeldung zu Telnet in FMO | open | 0 | Christian Rapkow | LC R
Connection Database | Verbindung zu Daten in FMO | open | 0 | Sandra Cayot | LC R
Wareneingang |  | open | 0 | Sandra Cayot | LC R
Einlagerung |  | open | 0 | Sandra Cayot | LC R | Database server is down
KT Kommissionierung I |  | open | 0 | Torsten Graf | LC R
KT Kommissionierung II |  | open | 0 | Sandra Cayot | LC R
KT Kommissionierung III |  | open | 0 | Holger Ellmann | LC R | Capa
Warenausgang |  | open | 0 | Christian Brand | LC R
Auslagerung |  | open | 0 | Steffen Benra | LC R
Änderung Packstück |  | open | 0 | Alfonso Mato | LC R
Abschluss Packstück |  | open | 0 | Alfonso Mato | LC R
Ettikettendruck |  | open | 0 | Alfonso Mato | LC R

## Blockers
Blocker Name | Description | Responsible | Start Date | Priority | Resolution Status
FMO Environment not ready for handhelds | Blocker for Connection FMO - LCR | Christian Rapkow | 2025-09-01 | high | in progress

## Index
Responsible | Status | Location
Dierk Michaelis | open | LCK
Christian Rapkow | in progress | LCR
Torsten Graf | done | LCH
Steffen Benra | blocked | LCM
Matthias Merk |  | GLC GER
Peter Löhlein
Holger Ellmann
Sandra Cayot
Diana Krauss
Christian Brand
Alfonso Mato
Carola Ebel
Denis Maric
Jochen Betzgen
Enrico